## timeline
PROJECT ID | : | QOS12345 |  |  |  | LEGEND:
PROJECT NAME | : | Queensbay Office Shoplots |  |  |  | Prediction
PROJECT TYPE | : | Commercial - Heavy |  |  |  |  | DELAY
PERSON IN CHARGE | : | Taki |  |  |  |  | EXACT
IN ADVANCE
START DATE | : | 2020-09-21 |  |  |  | Difference in predicted & actual durations
EXPECTED DEADLINE | : | 2022-06-01 |  |  |  |  | ACTUAL < PREDICTED
ESTIMATED DEADLINE | : | 2020-10-01 |  |  |  |  | ACCURATE
ACTUAL > PREDICTED
EXPECTED TOTAL DURATION | : | 622 | DAYS
CURRENT PROGRESS | : | 11 | DAYS
TASK | STATUS |  | START DATE (DD/MM/YY) | EXPECTED DURATION (DAYS) | PREDICTED END DATE (DD/MM/YY) | DELAY | ACTUAL END DATE (DD/MM/YY) | ACTUAL DURATION (DAYS) | DIFFERENCE (PREDICTED & ACTUAL) | COMMENTS | PREDICTED DURATION | expected - predicted
IN ADVANCE
Planning | COMPLETED |  | 2020-09-21 | 10 | 2020-10-01 | 2 | 2020-09-30 | 7 | -3 |  | 8 | 2
Demo Prep | COMPLETED |  | 2020-09-30 | 6 | 2020-10-06 |  | 2020-10-06 | 4 | -2 |  | 4 | 2
Demolition | ONGOING |  | 2020-10-05 | 19 | 2020-10-25 | [5 empty] | 14 | 5
Excavation |  |  |  | 5 | [6 empty] | -1 | 6
Concrete |  |  |  | 13 | [6 empty] | -1 | 14
Pre backfill |  |  |  | 3 | [6 empty] | -1 | 4
Framing |  |  |  | 42 | [6 empty] | -1 | 43
Roof |  |  |  | 22 | [6 empty] | -1 | 23
Plumbing |  |  |  | 42 | [6 empty] | -1 | 43
Windows |  |  |  | 24 | [6 empty] | -1 | 25
HVAC |  |  |  | 22 | [6 empty] | -1 | 23
Electrical |  |  |  | 13 | [6 empty] | -1 | 14
A/V |  |  |  | 6 | [6 empty] | -1 | 7
House wrap |  |  |  | 4 | [6 empty] | -1 | 5
Insulation |  |  |  | 19 | [6 empty] | -1 | 20
Drywall |  |  |  | 21 | [6 empty] | -1 | 22
Exterior stone |  |  |  | 15 | [6 empty] | -1 | 16
Exterior case work |  |  |  | 10 | [6 empty] | -1 | 11
Laundry/furnace room flooring |  |  |  | 24 | [6 empty] | -1 | 25
Hardwoods |  |  |  | 51 | [6 empty] | -1 | 52
Tile |  |  |  | 12 | [6 empty] | -1 | 13
Cabinets |  |  |  | 48 | [6 empty] | -1 | 49
Plumbing -hang sinks |  |  |  | 8 | [6 empty] | -1 | 9
Interior doors |  |  |  | 13 | [6 empty] | -1 | 14
Millwork |  |  |  | 3 | [6 empty] | -1 | 4
Interior painting |  |  |  | 46 | [6 empty] | -1 | 47
Stone Counters |  |  |  | 11 | [6 empty] | -1 | 12
Schedule Buffer |  |  |  | 11 | [6 empty] | -1 | 12
Decks |  |  |  | 19 | [6 empty] | -1 | 20
Interior doors- hang & hardware |  |  |  | 11 | [6 empty] | -1 | 12
Appliances |  |  |  | 2 | [6 empty] | -1 | 3
Plumbing |  |  |  | 4 | [6 empty] | -1 | 5
Electrical |  |  |  | 9 | [6 empty] | -1 | 10
Bathroom Glass |  |  |  | 5 | [6 empty] | -1 | 6
Garage Door dress up |  |  |  | 6 | [6 empty] | -1 | 7
FINAL Inspections |  |  |  | 1 | [6 empty] | -1 | 2
Wrap up |  |  |  | 28 | [6 empty] | -1 | 29
House Cleaning |  |  |  | 13 | [6 empty] | -1 | 14
Complete |  |  |  | 1 | [6 empty] | -1 | 2
Formulas:
ACTUAL DURATION (DAYS) = NETWORKDAYS([START DATE (DD/MM/YY)], [DELAY])-1
DIFFERENCE (PREDICTED & ACTUAL) = NETWORKDAYS([EXPECTED DURATION (DAYS)], [ACTUAL DURATION (DAYS)])-1
PREDICTED DURATION = NETWORKDAYS([START DATE (DD/MM/YY)], [PREDICTED END DATE (DD/MM/YY)])-1

## client front page
DOC DATE | NO OF DAYS USED | NO OF DAYS PLANNED | EXPECTED DEADLINE | PROJECT ID | PROJECT NAME | PROJECT TYPE | STATUS | REMARK
2020-09-21 | 11 | 622 | 2020-06-01 | QOS12345 | Queensbay Office Shoplots | Commercial - Heavy | Heavy